# Measures to Ensure Final Customisation Cost

PBVN has implemented the following controls to ensure the USD 447,600 represents the final customisation cost:

a)	10-month Product Walkthrough (Feb-Dec 2025) covering all modules, formally signed off 6-1-2026 confirming all gaps identified.

b)	All 75 BRDs documented with detailed specifications and broken into 222 deliverable items. Signed off by PBVN business departments.

c)	Fixed-price contract locked 22-12-2025 at USD 1,075,450. Fixed rate USD 350/man-day, no variation clause. Oracle bears effort overrun risk.

d)	Scope frozen 15-10-2024. Formal Change Request process requiring Steering Committee and ITSC approval for any additions.

e)	All current SBV requirements covered through 19 regulatory BRDs (25%). Any post-Feb 2026 regulatory changes managed as separate CRs.

f)	All integration points defined: IB/MB (ODI), CardZone (file/API), CITAD/NAPAS/VCB (message queues), SeaTech (API), OFSAA/Acumen/DMS.

g)	Maximised Oracle standard features. All 75 BRDs represent genuine gaps where standard features cannot meet requirements.

h)	Oracle committed to July 2026 delivery. Schedule: Apr 2026 (start), May-Jun 2026 (delivery/SIT), Jul 2026 (final), Aug-Sep 2026 (UAT), 31-Oct-2026 (go-live).

Any future requirements from unforeseen regulatory changes (after Feb 2026) or business expansion will require separate CR approval with independent budget.